ROMA HEALTH PROJECT:

ROMA HEALTH SCHOLARSHIP PROGRAM – RHSP

MENTORSHIP COMPONENT

Final Report for the year 2013

The third year of the mentorship component of the Roma Health Scholarship Program supported by Roma Education Fund (REF) was started on 1 December 2012 and was completed on 30 November 2013. The whole project was implemented according to the project proposal approved by the Open Society Foundations. In total, 11 months (excluding one month of summer holiday from 15th July until 15th August) of intensive work at three university schools of medicine in the Republic of Serbia (Belgrade, Novi Sad and Nis) provided opportunity for Roma students and their mentors for better professional development and inclusion in academic community.

The main goal of this component was to provide one year mentorship program for Roma students preparing for health professions (medical doctor, pharmacist, dentist) at high educational institutions in Serbia. Only Roma students enrolled in Roma Health Scholarship Program and who got ghant by REF were eligible for mentoring.

Objectives of the mentorship component were to:

- Provide support and help for Roma students in their professional, academic and personal development;

- Support inclusion of Roma students in academic and social environment and realization of their right for education;

- Support Roma students in participation of health promotion programs devoted to Roma communities and in development of effective public health policies for Roma health promotion.

ROMA STUDENTS IN THE MENTORING COMPONENT OF RHSP

In total 34 Roma students (Table 1) were involved in this project with 25 females and 9 males. Students were from three University centers: three of them from Faculty of Medicine Belgrade, 2 female students from Faculty of Pharmacy Belgrade, 19 of them from Faculty of Medicine Novi Sad and 10 students from Faculty of Medicine Nis. Unfortunatelly, this year we do not have students from the Faculty of Medicine in Kragujevac.

At the end of December 2012 we obtained the list of Roma students preparing for health professions (30 in total) who received scholarships by Roma Education Fund, and thus became eligible for a mentor. RHSP Coordinator for Serbia, Jelena Savic sent on March 7th to the Head of the mentorship component of the project a list of Roma students who additionally got scholarships (Svetlana Stojanovic, Boris Nikolic, Milena Alic and David Bahtijarevic). From a total of 34, twelve students were from previous years of the project, 2011 or 2012, while 22 of them were new students in the program. The majority were medical students (21), 7 pharmacy students, one dentistry female student, 4 of them are on special education program at the Medical Faculty in Novi Sad and one student in doctoral studies of public health also from the Novi Sad.

At the very beginning of the project, students were introduced to their mentors and then carefully read and signed the Code of Conduct for students and mentors (Annex 1) in order to be aware in details of their obligations and mechanisms of arbitration in case of disagreement. During January, February and March all of them sent it to the project manager. The formulation of the Code of Conduct came as a result of the experience in the first year of the project and of joint interview at the final meeting of the project held in Belgrade in November 2011. Usually one mentor was responsible for two Roma students, which is formulated by the requirements of the project, however, as only one female student was at PhD studies in Novi Sad and as it was an odd number of students at the Faculty of Medicine in Belgrade, that rule could not be applied for two mentors, and therefore they got one student each.

Student’s expectations from their mentors

All students involved in this project were obliged to write small essay (one page) about their expectations from the mentorship program which they later gave to their mentors and sent a copy to the project management team. They stressed that primarily they expect to establish good and friendly relationship with their mentors, expect help in learning process, organization of consultations with other lecturers, and that they need support in gathering skills for everyday practice of health professionals. Few students noted that they want help in scientific work – advice how to search literature, involvement in writing scientific articles and selection of meetings and congresses for their participation. Also, several of them expressed understanding and sympathy for the problems of Roma population in Serbia. Almost all students stressed that they expect help in personal development from their mentors, in terms of availability and understanding of their personal problems and advises how to overcome those, help in organization and planning of their time during study process, fun and other activities. It is very important that mentors were introduced with the expectations of their students, in order to be prepared for adequate responses during the mentorship program.

Student’s Personal Development Plan - PDP

As in the first two years of the project students were asked to make their own personal development plan (PDP) as a structured and continuous process that helps them to think about their own learning, performance and achievements and to plan for their personal, educational and career development. It is useful for students, as well as, for mentors. PDP presents a part of the professional portfolio or educational file of both students and mentors. The role of the mentor is to help students to make their own PDPs which they will later fill in and maintain (through their study and career).

The primary objective for PDP is to improve the capacity of students to understand what and how they are learning, and to review, plan and take responsibility for their own learning. Also it helps them to define goals and to evaluate progress in achieving those goals, to become more effective and independent in their work, to improve the learning skills and to pursue positive attitude towards learning, future education and career.

In total 29 of 34 students in the third year of the mentorship component of the project wrote their PDP. Unfortunatelly, five students did not send their PDPs, despite numerous reminders (by e-mail and by telephone) by the project manager.

PDP’s Template consists of 6 steps (Annex 2), and these are: current state definition, desired state definition, activities and resources needed to achieve the desired state, timeline, implementation and evaluation.

As a first step in the PDP, students defined their current state (Table 2), which was essential for measuring progress in the activities during the project life.

Regarding positive features, i.e. strengths, the students pointed out in the first place persistence and determination than responsibility and decisiveness. They also see themselves as ambitious, communicative, diligent, intelligent young people full of optimism. For the first time in the project the support of mentor was recognized as strenght especially by students who had already been several years in the project indicating the importance of the mentoring process. Regarding weaknesses the most students emphasized on the first place lack of self-confidence, poor organizational skills, than their emotional state, laziness and rashness. Some of the students identified as negative features that they are uncommunicative, stubborn, indecisive, shy, perfectionists and they do not have enough time to devote to out-of-school activities. Three of them said that they are hot-tempered and have stormy reactions. Concerning focus areas priorities on which they would like to work, i.e. to improve during the project life, in the first place is better management of their own time, than building of self-confidence and decisiveness, efficacy and thoroughness in studying, greater social activity, motivation, diligence, emotional stability, creativity, control of hot-tempered nature, as well as, improvement of linguistic skills (Table 2).

Table 2. Students’ current state

| What are my strengths? | What are my weaknesses? | What are the common feedbacks that I receive from others? | What are focus area priorities that I need to improve? |
| --- | --- | --- | --- |
| Persistent, determined (17)* | Lack of self-confidence (11) | Communicative, Sociable (11) | Better management of own time (9) |
| Responsible, decisive (14) | Poor organizational skills (10) | Intelligent, pametan (8) | Building of self-confidence (7) |
| Ambitious (7) | Emotional (9) | Responsible (6) | Efficacy, Thoroughness in studying (4) |
| Communicative (7) | Lazy (9) | Diligent (6) | Decisiveness (6) |
| Intelligent, capable (7) | Rash, Hot-tempered nature (7) | Persistent (6) | Greater social activity, communication (5) |
| Diligent (5) | Uncommunicative, asocial (6) | Witty, Happy (6) | Motivation (4) |
| Mentor support (3) | Stubborn (6) | Ambitious (5) | Diligence (4) |
| Optimist (2) | Lack of time (4) | Nice, honest (3) | Emotional stability (4) |
| Different (2) | Indecisive (3) | Stubborn (3) | Creativity (3) |
| Team player (2) | Shy (2) | Tolerant (2) | Control of hot-tempered nature (2) |
| Unique (1) | Perfectionist (2) | Leader (2) | Improvement of linguistic skills (2) |

*Total number of students who stated specific feature

As a second step in the PDP, students were asked to say what they wish to achieve and why, i.e. what are their objectives in the project and later in the lifetime. The greatest number of students in the first place said they want to improve their knowledge, oral and practical skills, and to gain better work habits in order to manage their time and to plan their activities better, to be more efficient and more thorough in learning, to increase chances of getting the job, to be more successful and to have better social status. In the second place students underlined the desire to be more decisive, with more self-confidence in order to create new opportunities for success, to be more respected in the society and to be better contributors to the society. When it comes to control of students’ hot-tempered nature they believe that reckless decisions and actions would be avoidable in that way and consequently their loved ones and the people around them would not be hurt. In fourth place of importance students would like to improve their emotional state in terms of being less sensitive and do not take too much to heart unimportant things as it will save them of unnecessary stress. Unlike in the previous two years, when most students saw themselves as members of non-governmental and student organizations through which they would like to promote the identity of the Roma people and to point out their marginalized position in the society, this year that was not the case. This could be explained by the fact that in the meantime they have already become members.

As a short-term goal, students would like at first place to pass remaining exams in the school year, to enroll in the next year and to obtain Bachelor’s degree, to write original scientific papers, to be a little more occupied with out-of-school activities (learning languages and improving musical skills), to begin with volunteering and humanitarian work in some of the student organizations, to travel and to have frequent meetings with mentor. Medium-term goals are to: be full-time students, enroll in postgraduate studies (preferably abroad), engage in scientific research work (projects, congresses, exchange of students) and become Roma activists. Regarding long-term goals, students see themselves as health professionals/specialists and proven experts in their field, as well as, they would like to contribute to the improvement of Roma health. Also, they would like to establish a stable family, to solve housing issue, to open own office and to constantly improve themselves.

Methods for meeting the goals, i.e. activities and resources which are needed for students in order to achieve the desired state are shown in Table 3.

This table clearly shows that students in the implementation of almost all activities recognize mentors’ help and see them as trustful personas which will help them to strengthen educational capacities due to better academic results, as well as personal and professional development. They are aware that scholarship is of exceptional importance and without it they would not be able to accomplish the majority of planned activities due to limited family budget.

Table 3. Activities and resources that students need to meet set goals

| Activities | Resources |
| --- | --- |
| Active learning (make more efforts, constant improvement, gain better work habits) | Scientific literature, Internet (electronic journals, online seminars), contacts with mentors, lectures, will, personal traits |
| To be engaged in scientific research (attend seminars, conferences, write scientific papers) | Scholarship, family budget, contacts with teachers, mentors, knowledge |
| To talk with mentor | Mentor |
| Start volunteering | Own will, contacts with project colleagues who are Roma activists |
| To control hot-tempered nature | Psychologist, mentor, self-control training, recreation |
| To be devoted to out-of-school activities | Time, scholarship, family budget, talent |
| To travel, to meet new people, | Contacts with teachers, mentors, scholarship, family budget, local NGO |

Students also defined timelines for achieving the desired state i.e. for meeting their set goals at the start of the project. They have already met a lot of them, which can be seen in more detailed scope from mentors’ report.

Students began with the implementation of PDPs in March 2013. They expressed satisfaction with PDPs which could be seen from the accompanying comments: ”The evaluation helps us to understand how we actually change what we wanted at the beginning. These forms should be filled more often, as in this project, as well as in other spheres of life”.

“Very interestingly done, simply compel a man to think a little bit about yourself. Well done. I love it!”

Roma students evaluation of the Mentorship component of RHSP

Until 10 November 2013, inspite of repeted reminders, 21 students out of 34 returned filled evaluation questionnaire (62% response rate). It should be noted that the evaluation form was the same for both students and mentors in order to enable comparison of their answers (Annex 3).

The first group of questions were related to time spent with mentors, the quality of consulttaions and the fact who initiated meetings. According to their personal assessment, students spent in average five to six hours per month with their mentors (minimum 2 hours, maximum 12, 16 or up to 20 hours) including telephone and e-mail contacts. They all stressed that this amount of time was enough according to their needs, except one female student who stressed that time she spent with mentor was not enough. Most frequently, initiative for contacts was from both sides, two students answered that the initiative was from mentor’s side.

The second group of questions refers to expectations, concerns and benefits gained from the whole mentorship component of the project. Student’s expectations were related to improvement of their professional and personal competencies, help in academic development and help in preparing exams. They also listed importance of help for easier learning, advices which help them in gathering new knowledge and skills, advices about lectures and exams and consultations with other teaching staff. Than, students expected to improve communication, networking with other teachers and professional development of academic networks. Their expectations were related to better adjustment to student’s life, easier overcoming of the problems, psychological support and assistance in critical situations; gaining confidence and overcoming fear of exams; engaging in non-governmental organizations, as well as assist in scientific research work.

Only one female student said that her expectations from this project had not been met, while all the other students who completed the evaluation questionnaire responded that their expectations had been met.

Benefit gained from the program included both professional and personal aspects are listed in Table 4.

Most important professional benefits for students were: better organization of their time, easier studying and help in preparing exams, support from their mentors in geting new knowledge and creation of academic network. As personal benefits from the mentorship program they stressed new contacts with people involved in project, new frienships, maturation, self-confidence, better communication and control in critical situation, as well as, development of responsibility, expertize and humanity.

Table 4. Professional and personal benefits for Roma students

| profesSional benefits | PERSONAL BENEFITS |
| --- | --- |
| Better organization of time, acquiring of new knowledge Easier curriculum overcoming, help in preparing exams and literature searching Better professional orientation in field of interest and topics for university degree work Acquiring of expirience in scientific research work Development of good and tolerant relationships, fight and devotion for their rights Cooperation with the professors and assistant professors without fear Success in passing important exams with the mentors’ help | New friends, new contacts with people involved in project; Maturation, self-confidence, better communication and control in crisis situation Development of responsibility, expertize and humanity Better organization of time, planning of obligations and respecting of examination period; More faith in themselves and self-esteem and breaking prejudice about uneducated Roma people, consciousness about their capabilities, satisfaction with themselfs, awareness of their own values; „Good experience from which I learned a lot“. |

According to opinion of Roma students, majority of goals of the mentorship component were achieved, particularly those related to professional development and gained knowlege, as well as, better contact with teaching staff and colleagues. Students’ opinion is that the program enhanced the process of career development except two of them who were not satisfied with the mentor. However, special attention deserves analysis of objectives which are only partly realized and related to the strategic direction for the career development of students, training for the skills necessary for daily practice and help in establishing contacts with the teachers – development of academic network (Table 5).

Table 5. Meeting the mentorship program component objectives by Roma students

| Questions | Not at all | Some -what | needs imprO-vementS | yes |
| --- | --- | --- | --- | --- |
| In your experience, did the program enhance the process of career development? | 1 | 4 | 4 | 12 |
| Do you feel that the program assists in developing career coaching skills for the mentors who participate in the program? |  | 3 | 8 | 10 |
| Did the program provide (sufficient) career strategy advice to students? |  | 4 | 5 | 12 |
| Did the program provide you with a sense of professional growth and development? | 3 | 1 | 3 | 14 |
| Did the program provide you with an opportunity to broader your knowledge and contacts with colleagues and teachers? | 1 | 4 | 5 | 11 |
| Did the program expose you to different facets of practice in health care institutions? | 6 | 5 | 3 | 7 |

There were no remarks on the mentorship component of RHSP and majority of students stated that it was good project helping them to achieve better academic achievements, that is very well organized and managed and that responds to Roma student’s needs.

When it comes to suggestions for improving the functioning of the project most advocated for earlier beginning of the project paralel with the beginning of the school year, that some mentors should devote more time to their students, that task of mentors must be better described, to organize joint trips in order to develop a better understanding and fellowship among students and mentors, and to develop a joint project on which both students and their mentors should work. Also, they stated as a problem organization of summer school and annual meetings during examination period due to their academic obligations.

Compliments of the project were very concrete and included the remark that the project made their studies easier, highlighting merits to the coordinator, mentors and funders for its implementation and special credits to some mentors as excellent educators. Finally illustrative quoted remark of one student: "Thank you all for allowing me to feel as special person in this project."

MENTORS IN MENTORSHIP COMPONENT OF RHSP

In the second half of December 2012 and in the first half of January 2013 16 mentors were selected. After awarding additional scholarships in March 2013 two more mentors were elected. For students who again received scholarships the selection of mentors was performed based on the evaluation of their work in the first two years of the project and expression of student’s desire to continue working with his/her mentor. For new students selection was based on the recommendation who would like to be their mentor and on communication with the colleagues from the faculties of health professions in Serbia.

Potential mentors filled application form with all important data and sent it later together with CV and short motivation letter with an explanation why they would like to participate in the project. Desirable characteristic such as openness, wilingness for cooperation and sensitivity to ethnic minority groups especially Roma people, motivation to help them to integrate more easily into the academic environment, and previous experience with the mentor were basis for selection.

Additional criterion for mentors selection was to teach in the same year their students registered because that way enabled mentors to help students in the learning process at their best. The limiting factor under the terms of the project was that a mentor has two students (so all students wishes could not be accepted).

From the previous project seven mentors left: Assoc. Prof. Dr Jelena Popadic Gacesa, Prof. Dr. Spela Golubovic and Prof. Dr. Marija Mihalj from the Faculty of Medicine in Novi Sad, Assist. Dr. Zeljka Stanojevic from the Faculty of Medicine in Belgrade, Assoc. Prof. Dr. Boris Djindjic, Prof. Dr. Stojanka Arsic and Prof. Dr Ivana Stojanovic from the Faculty of Medicine in Nis. We thanked all other former mentors for cooperation as some of the students were not satisfied with their mentors (Assist. Dr. Ana Sebenji and Assist. Dr. Smiljana Rajcevic), while there was no Roma students for teaching assistant Vesna Stojanovic Marjanovic from the Faculty of Medicine in Kragujevac.

Teachers and collaborators who signed up for mentors in this project are:

- Assoc. Prof. Dr. Nenad Stojiljkovic, physiology, Faculty of Medicine, Nis

- Prof. Dr. Katarina Ilić, pharmacology, Faculty of Farmacy, Belgrade

- Assist. Dr. Nataša Milošević, pharmacy, Faculty of Medicine, Novi Sad

- Assist. Dr. Boris Milijasević, Institute of pharmacology, toxicology and clinical pharmacology, Faculty of Medicine, Novi Sad

- Assoc. Prof. Dr. Matilda Vojnović, general medicine, Faculty of Medicine, Novi Sad

- Assoc. Prof. Dr. Dragana Milutinović, health care, Faculty of Medicine, Novi Sad

- Assoc. Prof. Dr. Tatjana Ćebović, biochemistry, Faculty of Medicine, Novi Sad

- Assoc. Prof. Dr. Slobodan Mitrović, otorinolaryngology, Faculty of Medicine, Novi Sad

- Assoc. Prof. Dr. Otto Barak, physiology, Faculty of Medicine, Novi Sad

- Assoc. Prof. Dr. Miodrag Drapšin, physiology, Faculty of Medicine, Novi Sad

- Prof. Dr. Vesna Turkulov, infectious diseases, Faculty of Medicine, Novi Sad and

- Prof. Dr. Ljubica Stojšić Džunja, anatomy, Faculty of Medicine, Novi Sad

In total 18 mentors were in the project this year (7 mentors from the previous year and 11 new mentors).

Out of 12 new applications and those who already participated in the project, the selection process was based on the decision by project cooridnator, assistant project cooridnator and national coordinator of RHSP. The selection process was completed by 18 January (15 March for additional two mentors) and all mentors were informed about it.

Old mentors started with the work from the beginning of January. In the second half of January, newly elected mentors were introduced with their obligations in the mentorship component of the project, they were connected ("paired") with their students and it was recommended to organize the first meeting. All mentors and students signed the Code of Conduct in the project which specifies their responsibilities and mechanisms for arbitration in case of disagreement and submitted it during January, February and March to the project manager. Also, mentors and students were asked to make individual and collective digital photos in order to create publications and for the promotion of the entire project and its mentoring component. List of all mentors included in the mentorship component is presented in Table 6.

Additionally selected mentors in the project based on mentioned criteria were:

Prof. Dr. Verica Avramovic, Histology and Embryology, Faculty of Medicine Nis who was paired with two students

Assist. Dr. Predrag Ostojic, Institute of Rheumatology, Faculty of Medicine in Belgrade, who was paired with one female student

As Prof. Dr. Marija Mihalj already had one student, and consearning the rule that every mentor has a maximum of two students, she was paired with one more student.

Professor dr Boris Djindjic, mentor from the Faculty of Medicine in Nis voluntarily accepted to work with Roma medical student Sasa Azirovic, who did not get scholarship but was willing to work with Boris. Project coordinator and assistant cooridnator organized meeting with Roma students enrolled at the Faculty of Medicine Belgrade University based on affirmative measure of the Government of Serbia and offered them a help during their studies, but only one first year female student Vanja Angelovski was interested in the project and therefore informed about it.

It is worth to mention that mentors take care of their students from the previous project cycle who did not get a scholarship this year, but they are still in touch with the mentors.

During the whole period of project implementation, both students and their mentors had intensive contacts. Mentors regularly reported about all project activities, first monthly to assess how well they started their activities, after that per three months, and at the end of the project they submited final reports which were used also in the project evaluation. All mentor’s reports are part of the project documentation (on Serbian language) and are available on request.

During summer holiday, from July 15th until August 15th was a break in the project implementation and both mentors and project team management were not payed.

Self-assessment of mentors – “How good mentor are you?”

One of the mentor’s tasks at the beginning of project implementation was to fill out a self-assessment questionnaire about their work, i.e. to have an insight to what extent they are good mentors for their mentees (Annex 4). All 18 mentors who participated in the project fill out mentioned form and submitted it to the project manager.

For each of 9 activities/strategies in self-assessment form, mentors were obliged to give an example from their practice which illustrates its use, as well as, to give suggestion for its improvement. Those activities include question about appreciation of individual differences among students, availability of mentors, use of active questioning which leed a mentee towards solution, strategy they use to build a scientific community, strategy they use to build a social community with students, did they celebrate a student’s achievements, development of mentoring skills, networking and with how many of their past students they are still in contact.

All answers were similar to previous year thoughts of mentors taking in account that seven of them are experienced mentors from the previous year of the project.

All mentors stressed that they appreciate individual differences among students and found it out as an important subject due to different students’ capacities for progressing and for fulfilling obligations. They stressed that there was a need for adjustment of the consultations to student’s needs and capabilities. They also stressed they have now more understanding and acceptance of differences among students, as well as they are more open in their approach to all students, not only those from ethnic minorities and they noticed that some students had problems in verbal communication and they tried to overcome it. When they were asked to give an example of doing this activity better or more, majority of them cited that probably more time for consultations will be useful, they are now more involved in activism against any form of discrimination and their lectures and exercises are more tailored to the needs of students and their level of understanding.

Mentors said that they respect the agreed time of consultation and they require the same from the students, although consultation often happened before the exam or exercises. Mentors are available to their students at the faculties where face to face encounter can be easily arranged. Also, they can be reached by telephone, e-mail, and some of them through social networks, students’ forums or online consultations. They asked students to respect schedule of consultations, however as a problem they found lack of adequate space or rooms for consultations with their students.

Mentors usually questioned themselves about conflict situations with the students and tried to find adequate solutions. They also tried to incentivise students for better planning of their time and to motivate them for participation in scientific work. They said that better and more could have been done in finding the right motivation and encouragement of the students and to explore the causes of the problems they had like fear or anxiety during the exam.

Construction of the scientific community is a very important part of mentoring and therefore they stated to follow the interest of students and include them in teams engaged in scientific research, they recommended interesting books and publications or meetings and courses about research problems. When asked what they could have done better, they said better conections with colleagues who are engaged in scientific research and more incentives for students to be engaged in this kind of work, although it was not always easy considering how medical studies are difficult and demanding.

When it comes to building social networks and community, mentors stimulated their Roma students to get involved in the Students' Club, worked on the development of their social responsibility especially for the Roma people and their local communities, and encouraged students to participate in extracurricular activities – going out and having fun. Mentors believe that they had to encourage them to work in NGOs and existing organizations at the Faculty though it would have been better for Roma students to form their own social group focused on specific tasks.

Talking about the remaining strategies that mentors practice in their work, it is important to note that they often celebrate the success of their students and with some of them are still in contact which represents a mentorship for life.

Mentors evaluation of the Mentorship component of RHSP

Project evaluation in this report is based on evaluation questionnaire filled out by mentors at the end of the project period in November 2013. The purpose of this evaluation is to determine whether the project justified invested money into professional and personal development of Roma students and whether it was tailored to their needs. Evaluation questionnaire (Annex 3) consisted of 12 questions divided into three groups.

Mentors sent completed questionnaire to project coordinator and assistant coordinator of the project who then analyzed the responses to the questions. Although it was anticipated that the questionnaire is anonymous, all mentors signed their names. It is particularly requested from mentors to give their comments and suggestions for project improvement in order to improve activities for the next year, to achieve better project results and to fit the needs of the students and mentors in greater extent.

All mentors returned filled questionnaire by 10 November 2013 and evaluation results of Roma students and mentors were presented at the final meeting held at the Faculty of Medicine Belgrade University.

The first group of questions related to time spent with student, the quality of meetings and the fact who initiated meeting. Mentors spent in average from 6 until 8 hours monthly (minimum 3 hours and maximum 10, 12 or even 18 hours monthly during preparation for oral exams or test).  Majority said that the time spent with the students was enough and adequate for student`s needs, one that was partially enough, and two that was not enough. The inition of the meetings usually came from both, but 6 mentors indicated that they were initiators of the meetings. An important note is that mentors noted more hours of consultation then students themselves.

Mentor`s expecations from the mentorship component are following:

- Ability to learn more about the students and difficulties encountered during their studies and building of mutual trust as very important aspect of mentoring.

- Mentors noted that this task was professional challenge for them, an opportunity for further professional development, for acquiring skills and knowledge which all leads to improvement of the pedagogical work of teachers at Faculties of health professions in Serbia.

- Help students to better manage their time, commitments, to overcome stage fright and fear and to successfully pass exams and tests.

- Introduction to the problems of Roma students during their studies, and

- Cooperation and friendship with the students, striving for higher goals which are reflected in the proactive participation for the foundation of Roma academic elite.

The second group of questions from the evaluation questionnaire included expectations, comments and benefits from the project. All mentors noted that their expectation from the project were fulfilled and they have no remarks on project organization, management and implementation. The biggest professional benefit for mentors is the opportunity to improve their pedagogical knowledge and skills through mentoring, to better take into account the characteristics and needs of students, as well as to recognize the cultural specificities of Roma students. When it comes to personal benefits they were related to friendship with Roma students that enriched mentors with the special kind of emotions and the fact that by helping students they also ennobled themselves as human beings (Table 7).

Table 7. Professional and personal benefits for mentors

| PROFESSIONAL BENEFITS | PERSONAL BENEFITS |
| --- | --- |
| Dissemination of pedagogical knowledge and acquiring of new experiences that make it possible to observe other aspects of working with students Consideration of the problems encountered by students and ways to overcome them; Work on the individual level with students which is not common in undergraduate teaching in medical faculties due to large number of students; Improvement of the communication and increased contacts with the colleagues; Professional development and recognition of the role of mentor; A better understanding of the problems of young people, the development of humanity and tolerance; Creation of a social network. | Valuable introduction to the culture and customs of the Roma community; Personal satisfaction for helping young colleagues to cope with the academic environment and for their better integration; New friendships with the students, high-quality and more intimate contact, a sense of satisfaction and fulfillment; A better insight into own capabilities, a sense of significance and importance. |

The fulfillment of the mentoring program component objectives of the project according to mentors is presented in Table 8.

Table 8. Meeting the mentorship program component objectives by mentors

| Questions | Not at all | Some-what | needs imprO-vementS | yes |
| --- | --- | --- | --- | --- |
| In your experience, did the program enhance the process of career development? | 1 | 2 | 1 | 14 |
| Do you feel that the program assists in developing career coaching skills for the mentors who participate in the program? |  | 1 | 1 | 16 |
| Did the program provide (sufficient) career strategy advice to students? |  | 1 | 5 | 12 |
| Did the program provide you with a sense of professional growth and development? |  | 1 | 1 | 16 |
| In your opinion, does the program provide mentors with greater appreciation of their significance as role model? |  | 1 | 1 | 16 |
| Did the program provide you with an opportunity to broader your knowledge and contacts with colleagues and teachers? | 1 | 4 | 3 | 10 |
| Did the program expose you to different facets of practice in health care institutions? | 3 | 5 | 5 | 5 |

According to mentors opinion, this component was very important for their development as teachers and all stressed that it helped them to improve knowledge, but also their contacts with other coleagues at universities. Involvement in this project was important for their career development and bring them more responsibility as a good role model for their student. However, like in the last year, mentors` opinion is that the project met all objectives except enough exposure of students to different facets of practice in health care institutions.

Many useful suggestions and comments were given by mentors how to improve project performace. Suggestion from mentors related to the beginning of the school year program due to the fact that in that case they can monitor student’s work better (it was also suggestion from last year) but ufortunately this was not possible to realize because of duration of student’s application and selection procedure. They stressed the need for multiple contacts, especially those who are new in the project because they are not familiar enough with their students. It would be important for them to define exactly the skills of their students and it would be good to consider successful presentation skills and public speaking skills.

Reccomendations for project improvement:

- Education of mentor with the skills of pedagogical work;

- Providing financial support for independent student projects;

- Providing incentives for students involvement in Roma NGOs focused on Roma issues;

- Both students and mentors need to be better informed about people who are involved in the project and better networking;

- Introducing students with the rules of electronic communication;

- More frequent meetings of students and mentors in order to know each other better and for exchange of experiences.

Finally, as a conclusion it was stated that the project is well designed and that its realization is constantly monitored. It provides students with the opportunity to improve their knowledge and skills, gain self-confidence and appriciate their own values. It was stated that the project is a major step forward improved professor – student relation in undergraduate studies at the Faculties of health professions in Serbia. One mentor said, "Good luck, and I hope for further good cooperation."

ACTIVITIES IMPLEMENTED IN MENTORSHIP COMPONENT OF THE RHSP DURING 2013

During the project implementation in 2013 cooperation with other components of the RHSP – advocacy component and media component was established and it was very close and successful. Also many activities related to the organization of meetings of the mentorhip component of the project, as well as, to the participation at meetings and conferences that are directly or indirectly associated with RHSP were organized.

The organization of the final meeting of the year 2012

The second final meeting of Roma students and their mentors from the previous project was held on 14 December 2012 in Dean’s building at the Medical Faculty in Belgrade. Although there were lack of financial resources for travel expenses and cocktails, national coordinator of RHSP, Jelena Savic helped us with the funds to organize final meeting. The meeting was not attended by all students and mentors because of the harsh winter with snowdrifts, so some were not able to reach or some were sick or had obligations at the Faculty, but the meeting and socializing afterwards were constructive and useful for exchange of experiences in this project. The guests were welcomed on behalf of the Faculty of Medicine and Center School of Public Health and Health Management, Prof. Dr. Vesna Bjegović, and then the national program coordinator Jelena Savic said several important facts about the project. Project Manager Snezana Simic introduced participants with the results of the project evaluation by both students and mentors, and depute project manager Janko Jankovic with students’ personal development plans. Then lively discussion was developed about the results of the project and suggestions for its improvement. After the meeting cocktail lunch was organized with informal socializing and getting to know each other better. Colleagues from the Media Center responsible for media component of the project attended the meeting, as well as RTS journalists from the biggest and leading national TV in Serbia. Together they made several interviews with mentors and students.

Organization of mentorship component meetings on the beginnig and at the end of the project implementation in 2013

The first meeting of Roma students and their mentors was organized on 26 March in the premises of main building, Faculty of Medicine Novi Sad University (Hajduk Veljkova 3, in feast hall of Deans’ building on the first floor). This was according to the suggestion from Roma students and mentors to change place of meetings and to allow other Faculties to provide hospitality for the project. Despite awful wether (snow with ice) almost all Roma students and mentors participated at the meeting with project coordinator and assistant project coordinator. Dean, Prof. Dr. Nikola Grujić welcomed guests and then mentor Prof. Dr. Marija Mihalj as host and representative of mentors from Novi Sad University talked about her mentoring experience and work with her students. Project coordinator Assoc. Prof. Dr. Janko Janković had a presentation on the topic of "Mentoring, roles of mentor and personal development plan for the students in RHSP program" in order to meet new students and new mentors with the characteristics of this component of the project and with obligations, while the assistant project coordinator, Prof. Dr. Snezana Simic participants introduced the present with the students expectations in the project. Publication – guide for mentors was distributed to all interested mentors, and also promotional Bulletin about the work during the second year of the project. After the meeting cocktail lunch was organized at the restaurant of the Medical Faculty in Novi Sad.

This meeting was beneficial for all participants in the project since all were not at the Winter School. They had the opportunity to be for the first time together, to meet eachother a little bit more, to exchange their experiences and to plan future obligations more realistically.

The second final meeting of Roma students and mentors was organized after project was completed, on 22 November, in the premises of Dean’s building, Faculty of Medicine Belgrade. The meeting was not attended by all students and mentros, as some were sick or prevented to come due their obligations (during the meeting, and shortly after three Roma students enrolled at the Medical Faculty in Belgrade through affirmative measure joined us). The guests were welcomed on behalf of the Faculty of Medicine, Vice Dean for Continuous Medical Education Prof. Dr. Vesna Bjegović, then by Head of the Centre School of Public Health and Health Management Prof. Dr. Dejana Vukovic. Unfortunatelly no one came from the Belgrade Open Society Foundation due to election process of the new national coordinator held in that period of time. Project Manager Janko Jankovic presented the personal development plans of students in the project, and the Depute Project Manager, Snezana Simic with the evaluation of the project by both the students and mentors. Then discussion about the results of the project and suggestions for its improvement came alive. Bulletin about the work in the third year of the project was distributed to all attendees. Colleagues from the Media Center recorded a part of the meeting and interviewed several this-year-mentees and mentors for making video report. At the end, we all hung out together for a cocktail lunch at the Institute of Social Medicine (building across the Dean’s Building).

Meetings of the project management team with mentors and students from the University of Belgrade

At the Institute of Social Medicine on 26 February and 3 October two joint meetings of mentors and students from the University of Belgrade were organized in order to better meet each other and to talk about any kind of isssues. From the Faculty of Medicine in Belgrade besides project manager and deputy project manager Assit. Dr. Zeljka Stanojevic and student Damir Bahtijarević attended both meetings. Mentor Prof. Katarina Ilic from Pharmacy Faculty attended the first meeting, while mentor Predrag Ostojic was at the second meeting. We also called the former RHSP benefitiaries and all Roma students who were enrolled this year and last year at the Faculty of Medicine Belgrade over affirmative measure. Only first-year student Vanja Angelovski responded to the call and was introduced with the happenings around the project.

Cooperation of Mentorship component with Advocacy component of the RHSP

From 9 until 16 January 2013, immediately after holidays, winter school "Sasto III" – Advocate school for Roma future health care professionals was held in Andrevlje, Fruska Gora and organized by the Association of Roma Students from Novi Sad, leading component representation RHSP. The presence at the winter school was mandatory for mentors and students with this year scholarships, but due to commitments and exams which start in January, not everyone could attend it. Depute Project Manager Snezana Simic had two presentations, the first referring to "Mentoring and role of mentors in the RHSP program", and second about "Public health activism", and Project Manager Janko Jankovic talked to winter school participants about      "Inequalities in health and socioeconomic determinants of health". The presentations were interactive, participants were very interested, asking questions and interested in different aspects of the mentoring component. Last year's mentor professor Stojanka Arsic spoke about her mentoring experience and work with students. She had a presentation on "Pedagogical- psychological aspects of the so-called small group of Roma students." Also last year's mentor from Nis, Ivana Stojanovic attended and this year's mentors Natasa Milosevic and Boris Milijašević from Novi Sad came for one day. School was attended by 10 students with this year's scholarships and one student with last year's scholarship. Newsletter was distributed for promotion of the project, and the current high school students were introduced with the possibilities offered by the mentoring component of the project.

At the request of the Association of Roma Students from Novi Sad who are responsible for advocacy and tutoring components professor Simic came in touch with a professors of chemistry and biology at the Faculty of Medicine, University of Belgrade (Karadzic Ivanka and Ivana Novakovic) for engagement of two Roma high school students for preparatory classes for admission into Faculty of Medicine in Belgrade. On that occasion the meeting was held on 11 May and the start of preparatory classes for high school students was agreed. They both enrolled at the Faculty of Medicine.

Cooperation with media component of the RHSP in 2013

Cooperation with the media component of the project during the entire project period was continuous. Representatives of this component, journalists and photographers recorded all events in which we participated and uploaded material on the web site of the Media Center which in that way made ​​the whole project and especially its components more transparent and contributed to the promotion of all activities with Roma students. Two short video coverage about the mentoring component of the project were made (http://www.mc.rs/Video_Temp/09-Mentori_4.zip).

We also helped media component in involvement of Roma students Manuel Ramanovic and his mentor, Nenad Stojiljkovic from Faculty of Medicine Nis for the filming of the documentary "Bridging the Gap". Premiere of the film and the panel discussion "Knowledge against discrimination" including a project manager Janko Jankovic were held on 31 May in the Media Center.

This year there were no press conferences throughout Serbia aimed at promoting of the project and its components due to the fact that future scholarships will be awarded only for former beneficiaries.

Meetings with RHSP partners in 2013

The Head of the mentoring component, Janko Jankovic participated in the annual meeting of the "Partners scholarship program for Roma health project" held in Sinaia, Romania, 4 and 5 July 2013. Also one representative from each component of the RHSP participated from Serbia.

Janko Jankovic in the panel discussion "Developing a new generation of Roma health professionals" dedicated to mentoring and advocacy components talked about the achievements, challenges and lessons learned from the mentoring component of the project. Experiences were exchanged with colleagues from neighboring countries (Macedonia, Romania and Bulgaria) where similar projects are in progress for several years and therefore their ideas and activities will be helpfull for improvement of the mentoring component in Serbia. Meeting and socializing after were constructive and beneficial for all partners in the project. Publication guide for mentors were distributed to all stakeholders, as well as the promotional Newsletter about the second year of the project in Serbia.

For the first time this year at the same place an international advocacy summer school for students was organized for RHSP beneficiaries from Macedonia, Serbia, Romania and Bulgaria (1-3 July). The head of the mentoring component was asked to make a list of the top 10 students and to grade them taking into account the selection criteria sent by Gabriella Kurti from the Open Society Foundations in Budapest. At the end three students from Serbia were chosen to participate in international summer school of whome student Milena Pantelic, RHSP beneficiary spoke about her experiences in the project at the regional meeting of RHSP partners.

National Board for the selection of RHSP beneficiaries

This year, like in the previous one Janko Jankovic took part in the National Board for the selection of RHSP beneficiaries who will participate in the fourth year of the mentoring component of the project. During the ten days of July, candidates were evaluated over the Internet. In total 60 students applied. In the premises of the Open Society Foundation on 23 July all members of the Board met to overcome the differences in the assessment of some candidates.

BASIC PROJECT INDICATORS

All basic process and outcome indicators listed in the project proposal were selected from mentor’s reports submited by mentor. Some of them were selected from evaluation questionnaire filled out at the end of the project period by students and their mentors. Also, other project documentation – checklists, diaries, presentations were used for calculation of indicators (Table 9).

Out of 34 Roma students in the mentorship component, 21 of them passed all exams and enrolled at the next year of study (one female student is at postgraduated studies in public health, II year), and four are candidates for a degree which is a significant success of students and their mentors. Six students have a very high average mark (over 9) and they are excellent students. Also, six students were actively engaged in scientific research of whome four presented their scientific papers at the national student congress/symposium and some of them are currently writting papers and are preparing to participate next year. Two female students were co-authors of the two abstract that were presented at the international congress on public health in Brussels, one student received Erasmus Mundus scholarship to continue his education in Ljubljana, while one student received Basileus scholarship for a student exchange, also in Ljubljana, Slovenia. 10 of them are very active in the work of Roma non-governmental and students organizations in their cities.

At the end of April the project manager and deputy project manager together with Roma students from all three RHSP generations wrote two abstracts (Roma knowledge about HIV and Evaluation of the mentorship component of RHSP), that Snezana Simic presented at the sixth European conference on public health held from 13 to 16 November in Brussels.

During this year Newsletter was printed for the promotion of the project and presented to both students and mentors at the final meeting in Belgrade (Annex 5), for now only in Serbian language. We will try to make next year a few copies in English language.

Also guide for the mentors was designed from the financial resources of this project in Serbian language (Annex 6, the first two pages). In the creation of the guide, besides the Head and Deputy Head of the mentoring component of the project colleagues from Center School of Public Health and Health Management also contributed for free and the publication came out in February 2013. The purpose of this publication is to provide a basic understanding of the mentoring in an academic setting, colored with the experience gained during the mentoring component process. All this required a lot of commitment and it was time consuming.

Values of the indicators for monitoring mentorship component results are presented in table 10.

Table 10. Student’s success during mentorship component implementation in 2013

| Indicators | values |
| --- | --- |
| 1. Number of students who completed academic year | 21 + 4 candidates for degree (one female student is writing doctoral dissertation thesis) |
| 2. Success of students measured by number of exams passed and average mark | In average passed 6 exams (5.7 precisely; min 0 – max 11) . Average mark in the range 6.3 – 9.4 |
| 3. Number of students who wrote paper for medical journals | 1 |
| 4. Number of students who wrote abstracts and participated at students national and international congreses | 6 (3 students from Nis and 3 from Novi Sad) |
| 5. Number of students active in Roma NGOs or in Roma communities | 10 |
| 6. Number of students who got Erasmus grant | 1 |
| 7. Number of students who got Basileus grant | 1 |
| 8. Number of students who will stay in program | We do not know yet |

Throughout the whole 2013 the mentors have been working intensively with their students. Activities in this component of the project were devoted primarily to consultations, mastering the curriculum and way of passing the exams. Mentors reports (two-month and three-month reports) show that mentors intensely held consultations and follow the progress of their students. Also in contact with their colleagues they tried to give students some clarifications or elaboration of some difficult areas and to encourage them in their studying efforts. Some students had health and family issues, and two students have been maintaining pregnancy which led to a break in the passing exams and therefore mentors and students invested extra effort to overcome these obstacles. Also, few students were in the prolonged training abroad which included missing of four examination periods.

The mentors were asked to state explicitly all possible problems in working with the students, but also to specify precisely which exams their students passed and which did not to make it easier for both mentors and project managerial team to track students development and progress. There is a problem with a student Elma Jasari who was out of reach from September and did not contact her mentor, Professor Dr. Marija Mihalj. The project manager was trying to get in touch with Elma but so far there are no positive results. He also informed about it the new national RHSP coordinator Jelica Nikolic.

Suggestions for Mentorship component improvements

Suggestions for improving the mentoring component of the project given by Roma students and their mentors in the evaluation questionnaire and during the meetings are as follows:

- Most insisted that the project should start with the implementation of the school year because it is the most critical period of adaptation for all students, especially for Roma.

- Students argued that mentors had to devote more time to their students, for organizing joint trips in order to develop a better understanding and fellowship among students and mentors and to develop a joint project (mentors said that it would be good to provide financial support for independent student projects).

- Mentors highlighted the need for more contacts/meetings, especially those who are new to the project because they are not enough familiar with their students. It would be important to define exactly the skills of their students like presentation skills, public speaking skills, as well as to learn the rules of electronic communication.

- Mentors advocated for education in pedagogical work as well as for better informing of  students and mentors who is involved in the project and for better networking among mentors and students.

Anyway, as it could be seen from the analysis of the project evaluation by students and mentors, all are satisfied with the organization of the project, with the results monitoring and the activities carried out and they believe that this program is of great importance for their personal and professional development.

In conclusion

It is important for whole education system in Serbia to become more open to multicultural approaches and for people to accept the fact that by belonging to other nationality or to minority does not mean being exactly the same, having the same cultural diferences, or having the same economic background as it stressed in position paper of the Roma Education Fund „Roma Inclusion in Education“ (2010).

All RHSP activities are recognized in the academic community of Serbia, more and more students are involved in this program, more mentors are interested to participate in it and those involved in the project unselfishly help Roma students to achieve better results. Also the number of Roma students who are enrolled through affirmative measure at the Faculties of health professions is increasing which indicates that the academic community has become more sensitive to their needs and expectations from the society. Finally, as in the two previous reports, it should be stressed that whole RHSP and its mentorship component provide significant contribution to the process od Roma inclusion in high education. The impact of good mentor goes far beyond his or her own boundaries. With improvement of mentors’ skills and students’ compliance with this component of RHSP, as well as, with wider promotion and acceptance of this program by Roma community, we can expect better participation and better results in years to come.

Belgrade

25. 12. 2013.

Annex 1.

KODEKS PONAŠANJA I RADA STUDENATA I MENTORA U PROJEKTU

„MENTORSKA PODRŠKA ROMIMA STIPENDISTIMA KOJI SE ŠKOLUJU ZA ZDRAVSTVENE PROFESIJE“

Ovim Kodeksom su definisane obaveze mentora i romskih studenata u projektu „Mentorska podrška Romima stipendistima koji se školuju za zdravstvene profesije“ kao i mehanizmi arbitriranja u slučaju nesporazuma ili problema u radu. Mentor/mentorka će zajedno sa romskim studentima/studentkinjama svojeručnim potpisivanjem ovog dokumenta potvrditi da su upoznati sa obavezama i da će ih se pridržavati tokom trajanja projekta. Potpisan Kodeks bi trebalo vratiti rukovodiocima projekta (profesorki dr Snežani Simić i asistentu dr Janku Jankoviću).

- Očekuje se da se tokom projekta mentor/mentorka viđa sa svojim studentima jednom nedeljno „licem u lice“ (4 do 6 puta mesečno), a da istovremeno održavaju i druge vidove komunikacije, telefonom ili imejlom. Tokom ovih konsultacija, oni razgovaraju o napredovanju studenta na studijama, pripremaju ih za polaganje ispita, kolokvijuma i seminara tako što im omogućavaju kontakte i sa drugim nastavnicima ili saradnicima u nastavi i rešavaju eventualne probleme koji mogu da se pojave tokom studija.

- Odnos mentora/mentorki i romskih studenata/studentkinja je odnos pun razumevanja, poštovanja i uvažavanja međusobnih razlika. Studenti i mentori poštuju zakazano vreme konsultacija, kao i druge obaveze koje su preuzeli tokom međusobnog dogovora. Mentori i studenti su obavezi da redovno komuniciraju sa rukovodiocem projekta i zamenikom rukovodioca projekta (da odgovaraju na imejl poruke i/ili telefonske pozive).

- Na samom početku projekta je potrebno da mentor popuni upitnik za samoprocenu “koliko sam dobar mentor“, da ga pošalje rukovodiocu projekta, kao i da radi na usavršavanju svojih mentorskih veština.

- Od romskih studenata i studentkinja se očekuje da na početku projekta napišu kratak esej (na jednoj strani) o svojim očekivanjima od ovog projekta.

- Mentor/mentorka takođe ima obavezu da sa svojim studentima/studentkinjama u prvom mesecu rada na projektu formuliše personalni plan njihovog razvoja na osnovu formata koji je preporučen i usvojen u ovom projektu i koji će im biti dostavljen. Realizaciju ciljeva personalnog plana razvoja potom zajednički prate.

- Mentor/mentorka pomaže studentima/studentkinjama ako su zainteresovani za naučno-istraživački rad tako što mu lično, ili u saradnji sa drugim kolegama, pomaže u izboru teme, pretraživanju literature, kritičkom čitanju literature i pisanju studentskih radova. Potrebno je romske studente i studentkinje stimulisati i motivisati da učestvuju na kongresima studenata medicine i stomatologije sa tim radovima ili da ih publikuju, da konkurišu za domaće i međunarodne stipendije, i da usavršavaju znanje jezika (posebno engleskog jezika).

- Od mentora/mentorki se takođe očekuje da romske studente i studentkinje stimulišu da se angažuju u radu nevladinih organizacija, posebno onih koje se bave unapređenjem zdravlja Roma u Srbiji.

- Svi mentori i svi studenti u ovom projektu imaju obavezu da prisustvuju i učestvuju u radu sastanaka koji će biti organizovani na početku projekta (prva nedelja marta meseca) i na kraju projekta (poslednja nedelja novembra meseca) na kojima će se razgovarati o načinu rada na projektu, dostignućima i problemima u radu. Posle prve polovine projekta, mentori/mentorske i romski studenti/studentkinje popunjavaju evaluacioni upitnik, kao i na završetku projekta. Tokom projekta će biti organizovan monitoring rada mentora/mentorki sa romskim studentima/studentkinjama.

- U slučaju da se pojave problemi u radu mentora i romskih studenata, na zahtev studenta ili mentora može doći do promene mentora sa obrazloženjem zašto se to radi i nakon pokušaja da se međusobni problemi ili nesporazumi reše.

Datum:	 _____________			Tamara Savu, studentkinja

______________________________

Asis. dr Željka Stanojević, mentorka			Damir Bahtijarević, student

________________________			______________________________

Annex 2.

Personal Development Plan Template

| What is my current state? |
| --- |
| What are my strengths? | 1. 2. 3. |
| What are my weaknesses? | 1. 2. 3. |
| What are the common feedbacks that I receive from others | 1. 2. 3. |
| What are focus area priorities that I need to improve? | 1. 2. 3. |
| What is my desired state? |
| What do I want to improve? | 1. 2. 3. |
| Why do I need that? What does it give me? | 1. 2. 3. |
| What are my short-term goals (up to one year)? | 1. 2. 3. |
| What are my medium-term goals (2-5 years)? | 1. 2. 3. |
| What are my long-term goals (up to 10 years)? | 1. 2. 3. |
| What is needed to achieve desired state? |
| What activities do I need to take for achieving the goals? | 1. 2. 3 |
| What are the possible resources for achieving the goals? | 1. 2. 3 |
| Timeline |
| Schedule of activities | Focus area 1 Day and time: Focus area 2 Day and time: Focus area 3 Day and time: |
| Deadline for achieving the desired state? | Focus area 1 Start date: Short-term goal: Medium-term goal: Long-term goal: Focus area 2 Start date: Short-term goal: Medium-term goal: Long-term goal: Focus area 3 Start date: Short-term goal: Medium-term goal: Long-term goal: |
| Notes/comments/suggestions/other |

Annex 3

MENTOR / STUDENT EVALUATION FORM

To help RHE fund to maintain and improve the Mentorship component of the RHSP, we request that you complete and return the following program evaluation form. Please return filled questionnaire electronically to рrofessor Dr. Snežana Simić (snezanas@eunet.rs) or to assistant professor Dr. Janko Janković (drjankojankovic@yahoo.cоm).

This evaluation is being completed by the (check one):

а) Student				b) Mentor

Name and surname (optional): _______________________________________________

1. How much time, on average, per month has you spent with your mentor/student?  ____________ (in hours)

How was it spent? ________________________________________________________

2. Did this time commitment suit your needs?

YES				NO

3. If answer is NO, it was: 		a) too long, or 			b) too short

4. Which one usually initiated the meetings?

а) Mentor				b) Student				c) Both equally

5. What expectations did you have from the program?

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

6. Have these expectations been met?			YES			NO

7. If answer is NO, way is that?

__________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

8. Do you have any concerns about the program? (Please give examples and explain)

______________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

9. What do you feel you have gained from this program?

а) professionally____________________________________________________________

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

б) personally _______________________________________________________________

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

10. Please rank you answer for each question. Additional feedback is welcome and can be submitted on separate sheet provided at the end of this evaluation form.

| Question | Not at all | some-what | Needs improvement | YES |
| --- | --- | --- | --- | --- |
| 1. In your experience, did the program enhance the process of career development? |  |  |  |  |
| 2. Do you feel that the program assists in developing career coaching skills for the mentors who participate in the program? |  |  |  |  |
| 3. Did the program provide (sufficient) career strategy advice to students? |  |  |  |  |
| 4. Did the program provide you with a sense of professional growth and development? |  |  |  |  |
| 5. In your opinion, does the program provide mentors with a greater appreciation of their significance as a role model? |  |  |  |  |
| 6. Did the program provide you with an opportunity to broader your knowledge and contacts with colleagues and teachers? |  |  |  |  |
| 7. Did the program expose you to different facets of practice in health care institutions? |  |  |  |  |

11. Please give suggestions on how to enhance the program.

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

12. Please add any additional comments you may have.

Thank you for your assistance!

__________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Annex 4.

SELF-ASSESSMENT: How good mentor are you?

| ACTIVITY / STRATEGY | QUESTION / TASK | EXAMPLE | WHAT COULD BE DONE BETTER? |
| --- | --- | --- | --- |
| Appreciate individual differences | Give and example of an incident that illustrates your acknowledgement of individual difference |  |  |
| Availability | Give and example of the strategy you use to be available to your students/staf |  |  |
| Questioning | Describe how you last used active questioning to leed a mentee towards solution |  |  |
| Building scientific community | Describe a deliberate strategy you use to build a scientific community in your group |  |  |
| Building social community | Describe a deliberate strategy you use to build your group as a social community |  |  |
| Celebration | When did you last celebrate a student/staff member’s achievements? How did you celebrate? |  |  |
| Skill development | Describe steps you take to develop the critical writing and presentation skills of your students/staff |  |  |
| Networking | Describe one example of how you have introduced each of your students/staff into the scientific network of your research area |  |  |
| Mentor for life | How many of your past students/staff are you contact with? |  |  |

Annex 5. Mentorship component Newsletter

Annex 6. Guide for mentors of the Mentorship component of RHSP

# Text boxes

Faculty of Medicine Belgrade University

Center School of Public Health

and Health Management