Roma Students Association

Roma Health Scholarship Program (RHSP)

“Overcoming obstacles in entering Medical Universities for Roma high school students in Serbia“

-1st INTERIM NARRATIVE REPORT-

Reporting period: November 2011-10 April 2012

# INTRODUCTION

This report is the 1st interim narrative report on the implementation of the project  “Overcoming obstacles in entering Medical Universities for Roma high school students in Serbia“ .

The Project is within the framework of the Roma Health Scholarship Program (RHSP), supported by the Roma Education Fund (REF), and its implemented in Serbia from 1st November 2011 to 31st July 2012 (9 months).

Objective of the Project is to ensure better access to Medical Universities for Roma high school students in Serbia, by organizing comprehensive program for overcoming gaps in knowledge in biology and chemistry/mathematics from secondary school and preparation for passing the entrance exams at universities.

IMPLEMENTATION OF THE PROJECT BY ACTIVITIES

  - Signing memorandum of understanding /letter of support with relevant authorities

In the first week of Project implementation, the Project Team sent a letter to the Ministry of Health, Ministry of Education, Ministry of Human and Minority Rights and Roma National Council asking them to support the Project in written.

Written support to the Project was crucial to raise the level of schools’ interest in participation in the Project as secondary schools are our main channel to reach potential candidate teachers and Roma students.

The Project Team took comprehensive advocacy action to get the support letters using previously established connection and through persons indirectly influencing the decision makers in the Ministries.

Efforts where successful and on 30th November 2011 a letter of support from Ministry of Human and Minority Rights was issued. The letter, inter alia, stated “The role of secondary schools and medical faculties in raising motivation of teachers and Roma students to join program is vital for raising the number of competent Roma health professionals”.

On 16th December 2011, the Ministry of Education issued a letter to educational institutions titled “Call for joining RHSP program” which asked secondary schools to encourage potential candidate teachers and Roma students to apply upon a call of the Roma Students Association.

On 21st November 2011, the Roma Students Association signed the „Memorandum of understanding in implementation of campaign for spreading information on program for preparation of Roma students for medical studies” with the Roma National Council.

The Roma National Council has a database of more than 600 Roma high school students in the country who are the grantees and/or where candidates for the scholarship program since it was established 2 years ago.

This database helped to track schools where most of the Roma medical students are concentrated and to focus the attention on these schools in promoting call for students and teachers.

Also, if a small number of Roma students would apply, meetings with them for raising motivation for university education would be organized, using the Roma National Council database. Fortunately, 30 Roma students have been included in the tutorship program, and there was no need to organize motivation meetings to raise the number of applications.

Ministry of Health nevertheless did not reply on our request for support letter, but that did not jeopardize the project as we already had support from Ministry of Education.

  - Open call for candidate teachers and students

An open call for teachers and Roma students from medical schools, gymnasiums  and other eligible secondary school for entering medical studies (chemical, agricultural, economy) was announced on 16th December 2012 and lasted until 31st December(10 working days).

The call included:

- Text of the call an A3 format poster (for announcement boards in schools)

- Text of the call on A4 format copy paper

- Application forms for candidate teachers and Roma students

- Promotional poster for raising motivation of Roma students to continue studying                        medicine at universities

- Promotional flyer on the Preparatory courses for entering medical studies

- Support letters from the ministries and the Roma National Council

The open call was send by post in hard copy and by e-mail to the addresses of all 28 secondary medical schools in Serbia, 83 gymnasiums and 108 other secondary schools (Agricultural, Chemical...) that provide professional courses eligible for entering medical studies at universities.

- Outreach campaign

  - Direct contacts with Medical schools/dissemination call to schools

Three days after the call was disseminated to secondary schools by post and e-mail, the Project Team had a telephone conversation with all 28 medical schools in the country to check whether they had received the letter, and to ask the principles to encourage teachers and students in their schools to apply.

A week after the first phone call, we again contacted those medical schools that we know the RHSP beneficiaries, who are completing the secondary school in 2011/2012 academic year, are attending. These schools are reminded about the call and asked to assist the students and teachers in filling in the application form.

  - Radio and TV broadcasts

Radio and TV interviews and broadcastings occurred during the last 2 weeks of the open call for candidate teachers and students, aiming to spread the information about the call and raise motivation of potential candidates.

Due to the shortage of time, which was caused by general delay of the Project, less broadcasts than planned where implemented: out of 8 TV broadcasts planned in the project proposal, we managed to conduct 5, and out of 10 Radio broadcasts, 6 have been conducted as listed below:

| Name of the media | Date and time | Duration of broadcasting | Conducted by |
| --- | --- | --- | --- |
| Radio Alibunar, Alibunar | 15 December 2011 | 10 minutes, recoding, broadcasted same day in the evening | Project coordinator and monitoring expert |
| Radio Belgrade, Belgrade | 18 December 2011 at 13:00 h | 5 minutes, recoding broadcasted at 20:00 h in news | Project coordinator |
| Radio Bečej „Stari Bečej” | 21 December 2011 at 12: 15 h | 1 hour, live | Monitoring and RHSP role model student Ms Natalija Mitrovic |
| Radio „Točak“ Valjevo | 28 December 2011 at 14:00 h | 25 minutes, recording broadcasted on 29 December | Monitoring expert and RHSP role model student Ms Natalija Mitrovic |
| Radio OK Vranje | 29 December 2011 | 30 minutes, recoding broadcasted after | Project coordinator |
| Radio Kragujevac | 30 December 2011 at 9:00 am | 10 minutes, live | Monitoring expert |
| TV Vojvodina Novi Sad | 19 December at 10:00 | 1 hour | Project manager project coordinator and monitoring expert |
| TV Becej | 21 December 2011 at 15: 00 h | 30 minutes, recoding broadcasted afterwards | Project coordinator and roll model student Dajana Mihajlović |
| TV Beograd 2 | 25 December 06:00 | 1 hour | Project manager project coordinator and monitoring expert |
| TV Vranje, Vranje | 29 December 2011 at 13:00 | 30 minutes, broadcasted in the evening | Project coordinator |
| TV Kragujevac | 30 December 2011 at 11:30 am | 15 minutes, recording broadcasted afterwards | Monitoring expert |

  - Designing and printing out posters and leaflets

Two types of posters were developed: Poster 1 – call for candidate teachers and Roma was printed in 300 copies and distributed to 209 secondary schools, 55 Roma NGOs in Serbia, 9 non-Roma NGOs, 15 Roma municipality coordinators and 29 county representative offices of the Ministry of Education.

Poster 2 was developed to raise Roma students’ motivation to continue the medical studies at universities. For that purpose, we have organized a photo shoot of role model RHSP grantees Dejan Dimitrov and Natalija Mitrovic, a student with Roma babe, in the Clinical Centre of Vojvodina. The best photo was chosen and used for the design of the promotional poster with a massage „Prepare yourself and stand in line with life“. The poster was printed in 1000 copies and sent to secondary schools, Roma NGOs ... as in case of the Poster 1 with a call for candidate students and teachers.

  - Dissemination of Project information on the internet

Within the advocacy component of the RHSP, the grantees’ blog on internet http://rhspserbia.wordpress.com/ has been created, where Tutorship is a separate component. All calls and information about the ongoing project are regularly updated.

Calls for candidate teachers and students have also been posted on the Roma Students Association web presentation www.urs.co.rs

Partner organization - Media Center Belgrade in charge of the media component has posted the call for teachers and Roma students on their website, as well short information about the Project on the following link: http://www.mc.rs/stipendije-za-ucenikece-i-studentekinje-romske-nacionalnosti-za-obrazovanje-u-oblasti-medicinskih-nauka.2379.html

  - Disseminating information through other actors

In addition to secondary schools, information about the Project and open calls for potential candidate teachers and Roma students has been disseminated by post and e mail through:

- 15 local municipality coordinators for Roma issues

- 23 state offices of the Ministry of Education

- 15 mentors on the DILS program of the Ministry of Education

- 4 monitors on the Project “Inclusion of Roma Students in Secondary Schools in Vojvodina” of the Secretariat for Education of the Autonomous Province of Vojvodina

- 55 Roma NGOs throughout the country

- 9 most important non-Roma NGOs

- 2 Trade unions of employees in education

- 2 National associations of secondary school students

- 1 National Association of teachers

In total, 122 post letters have been send to the “other“ actors with enclosed call for candidates and promotional posters, leaflets and copies of the support letters from the Ministries and the Roma National Council.

- Selection of candidate students and secondary school teachers for individual classes to overcome gaps in knowledge

The open call for candidate teachers and Roma students was closed on 30th December 2011. The Selection Committee comprised of:

- Jelena Kris Piger-Secretariat for Education of the Autonomous Province of Vojvodina

- Marija Aleksandovic-Roma National Council

- Dejan Dimitrov-Representative of RHSP grantees

- Miroslav Nikolic-Monitoring expert

- Nenad Vladisavljev-Project manager

The meeting was held in Novi Sad on 5th January 2011, registering 56 teacher applications and 20 Roma students’ applications.

The Selection Committee advised to extend the open call until 20th January, for the following reasons:

- The Call was opened partly on time when some schools in the country did not work (from 24-31 December, therefore teachers and students did not have enough time to apply.

- Even though a considerable number of teachers applied for 8 Roma students, there were no applications from teachers from their municipalities. Organizing individual classes with teachers from other municipalities is technically very hard to implement due to the travel required.

- There were still 10 places for candidate students open as only 20 students applied

The Project Team complied with the suggestions of the Selection Committee and the open call was extended until 20th January, which proved to be a right decision.

On 25th January 2012, the second meeting of the Selection Committee took place in Novi Sad with same members participating as on the 1st meeting.

The Selection Committee registered 82 teacher applications (8 male and 74 female) and 29 Roma students’ applications (7 male and 22 female); 111 applications in total.

Teachers:

- Out of 82 applicant teachers coming from 27 municipalities, 28 are biology teachers, 34 are chemistry teachers, 19 are math teachers, 1 from other subject which is not eligible for call.

- 16 applicant teachers are employed in Gymnasiums, 6 in Chemistry schools, 4 in Economic schools, 12 in Agriculture schools,  42 in Medical secondary schools, while 1 teachers was unemployed and 1 was from an elementary school. These 2 where ineligible for the call

- 80  teachers met the eligibility criteria to participate in the program (Requirements for the applicant-teachers was to teach biology/chemistry/mathematic minimum 3 years in eligible secondary school, commitment to overcome difficulties of Roma students in education expressed in a motivation letter), while 2 teacher applicants were not taken into consideration as they are not employed in schools eligible for studying medicine (1 from elementary school and 1 unemployed)

Roma Students:

- 29 Roma student applicants where from 14 municipalities in Serbia, 2 from Gymnasiums, 2 from Chemistry schools, 25 from Medical secondary schools

- 17 students wished to enter general medical studies, 4 students - pharmacy,  2 Roma applicant student - dentistry, 1 student - special rehabilitation, 1 student - health care, 4 students - vocational studies at higher medical schools

- 13 students were interested studying at the Faculty of Medicine in Novi Sad, 12 at the Faculty of Medicine in Nis, 2 at the Higher Medical School in Zemun, 1 at the Higher Medical School in Cuprija and 1 at the Faculty for Pharmacy in Belgrade

Concussion:

- There were eligible teacher applicants from 26 municipalities, while there where Roma students from 14 municipalities. Teacher applicants from 12 municipalities were not taken into consideration because there were no applicant students.

- In cases where there was more than one teacher applicant for the same subject  per municipality, a teacher who was recommended by students was selected

- In cases where there was more than one teacher applicant for same subject, but there were no recommendations from students stated in students application form, a teacher from gymnasium was selected, as the program of courses for medical faculties entrance exam is a gymnasium program

- There was no teacher applicant for one candidate (Igor Ognjanovic), as anatomy and physiology are tested at the entrance exam for the Vocational Medical School in Nis. Therefore, teachers for this candidate needed to be engaged after the open call, but we did not managed to find interested teachers before March

Based on the above students’ desires for specific studies and course requirements for entering such studies, the Selection Committee made a selection for individual classes to overcome gaps in knowledge as follows: 15 biology teachers, 17 chemistry teachers and 4 candidate math teachers; 36 teachers in total out of 80 eligible teachers that applied

  - Introduction meeting with successful applicant students and secondary school teachers

On 4th and 5th February, in the Novi Sad Hotel in Novi Sad, a meeting was held with the selected students and teachers. Due to extreme snow weather conditions, and because traffic in many parts of the country was blocked, only 20 students out of 29 selected and 18 teachers out of 36 selected attended the meeting; 38 participant students and teachers in total.

Purpose of the meetings was as follows:

- Introduction to  the Project, roles on the Project, expectations and monitoring instruments

- Breaking barriers between students and teachers and getting the project participants more familiar with each other

- Signing contracts with teachers and students

Day 1 – 4th February

The meeting started after lunch with a welcoming speech by Nenad Vladisavljev - the Project Manager, followed by a presentation of the RHSP program and its components by Jelena Savic-REF country contact person for RMUSP and RHSP scholarships. The first 90-minutes session was finished with detailed presentation by Miroslav Nikolic – a monitoring expert of the tutoring component of the RHSP program, timeframe and expectations from teachers and students.

In Session 2, participants were divided in 2 mixed groups (students, teachers) according to municipalities, who participated in a workshop aimed at breaking barriers among the participants. The teachers and students had an opportunity to present their personal aims and to work on joint problem solving set by trainers in second part of workshop.

Day 1 was finalized with a session on expectations. The teachers and students had an opportunity to express their expectations from the other party – students’ expectations form teachers and teachers’ expectations from students.

Students expected from teachers to smile, respect, understanding and clear massages. Teachers expressed that they expect from students knowledge, effort, respect, positive attitude and responsibility.

A discussion that followed articulated challenges for future work as follows: quantity of subject matter to be learned, lack of interests of students, non conscious discrimination by teachers.

Day 2 – 5th February

The first morning session on Day 2 was dedicated to workshops for planning future steps and timeframe. Teachers, students and ARS agreed that 16 classes of individual work need to be finished within 4 weeks after the meeting as preparation for the entrance exams on majority of medical faculties starts at that time.

The second morning session was about monitoring and evaluation instruments that will be used by the monitoring expert on the Project. Teachers and students were informed on how to create individual plan of achievements of each student, when and how they need to test students’ progress, how and when to file a report to the monitoring expert...

The meeting was followed by questions by teachers and students. The teachers asked a question what topics they need to cover with students in 16 classes. It was explained by   the Project Team that their role is to overcome gaps in knowledge from secondary school so that the students can attend preparation at universities from March without difficulties.

Some of the teachers that have more than one students asked if they could work in group, which was denied  by the Project Team as this is an individual component of the program.

The students asked about the teaching material from secondary school and the Project Team replied that there are costs for this purpose, but students need to have receipts for it. It was agreed with the students that the teachers will take on the responsibility to purchase teaching material, which will then be reimbursed by the Roma Students Association.

The final session of the meeting was dedicated to the work plan. The teachers and students were divided in groups: teachers-listed students for classes and they discussed how often within 4 weeks and where the classes will take place (teacher’s home or student’s home or school).

It was concluded at the end of this session that the fact that schools were closed due to the extreme weather conditions is an advantage for the project as the students and teachers can dedicate their attention completely to the individual classes to overcome the gaps in knowledge.

- Individual classes to overcome gaps in knowledge in biology,  chemistry and mathematics with secondary  school teachers

After the introductory meeting, the teachers and students who had not participated in the meeting were either visited by the monitoring expert or instructed by e-mail and phone.

In the meantime, one student, Ms. Mirela Novakovic, decided not to continue with the studies. The Project Team talked to her and her parents, but could not manage to change her decision to give up.

Therefore, 27 students in total (we did not find teachers for individual classes in anatomy and physiology for student Igor Ognjanovic before March) and 36 teachers joined the project and they had 4 weeks, i.e. until 5th March to conduct 16 hours of individual classes to overcome gaps in knowledge.

On the start, the teachers tested the gaps in knowledge of each student.

Each teacher created a test of 30 questions covering topics in courses covered during 4 years of secondary education. In general, students scored between 40% and 50% correct answers on the test. Based on the results, each teacher created an individual plan of achievement-what topics the student needs to cover for the next 16 hours of classes. Every teacher reported the results and the plan of achievement to the monitoring expert in a form previously developed for this case.

After half (8 classes) of the undertaken classes, the teachers placed a student progress test and reported to the monitoring expert (second report), and then at the end of the 16 classes (final report), teachers placed a test again. Some of the teachers asked for extension of the deadline to conduct 16 classes until 15th March due to objective difficulties, which was accepted by the Project Team (please see section on monitoring and evaluation).

In the first half of the course, the students were 66% efficient in average on Test 1, while in the second phase of the individual course, the total average score showed was 72% on Test 2, or 69% in total.

We consider that these data are not completely relevant to give the estimation of the students’ knowledge level as the teachers do not use the same standardized methodology in testing. Nevertheless, the data could show the following:

- In general, as the course developed, the students tended to work more on their progress

- Data can be used for tracking individual cases where there is no considerable progress in order to provide specific students with more attention

Better insight in the students’ progress will be available after the results of the Test 1 become available from the tutoring component, which is expected in mid April (after the tutors send their first reports). If the results of some students who had not progress enough on individual classes prove to be similar in tutoring classes, they will be provided with additional attention from their secondary school teachers.

  - Group preparatory  courses  at  medical faculties

Group preparatory classes are organized by medical faculties each year for all interested students and they are charged by the faculties.

At the Faculty of Medicine in Novi Sad, the group preparation course started on 26th February, and at the Faculty of Medicine in Nis and Faculty of Pharmacy in Belgrade, it started on 3rd March.

We had no students interested to enter the Faculty of Medicine in Kragujevac.

In the meantime, after the individual classes to overcome gaps in knowledge where finished, 2 new Roma students - Milena Alić and Miloš Segedi asked to join the Project. As we had 2 free places, we accepted their applications.

At the beginning of the group preparatory course at medical faculties we had 30 Roma students in the program in total.

13 students were included in the group preparatory course at the Faculty of Medicine in Novi Sad, 12 Roma students at the Faculty of Medicine in Nis, and 1 in Belgrade at the Faculty of Pharmacy.

There were 4 students interested in studying at the higher medical schools/vocational (1 in Nis, 2 in Zemun, 1 in Cuprija), but higher schools do not organize group preparatory courses, therefore we decided that these 4 students will be covered with tutoring classes only.

Group preparatory courses are organized in the premises of medical faculties during weekends.

- In Niš, on Saturdays: Biology from 09-12 h, Chemistry from 12-15 h,

- In Novi Sad, on Sundays: Biology and Mathematics from 09-12 h, Chemistry and Health care from 12-15 h

- In Belgrade, on Saturdays at 10-15 h Mathematic, and on Sundays at 10-15 h Chemistry

The Project Team visits each preparatory course when the travel cost for students who travel are reimbursed.

  - Tutoring classes with University teachers/Tutors

Purpose of tutoring classes is to provide additional support to Roma students in overcoming difficulties on group preparatory classes and understanding the eliminative logic of tests for the entrance exam.

A number of meetings took place in February and March with the Faculties of Medicine in Nis and Novi Sad, resulting in signing a contract with both faculties on the rights and obligations on tutoring classes.

It is agreed with the Faculties that tutoring classes will be organized in small groups of up to 6 students; on the same day after the group preparatory course takes place, i.e. from 15-17 h according to the following pronciples:

Week 1                          Week 2                                      Week 3                              Week 4

15-17 h                          15-17 h                                      15-17 h                               15-17 h

Tutoring classes           Tutoring classes                       Tutoring classes               Tutoring classes

In 2 groups                    in 2 groups in chemistry        Biology in 2 groups          in 2 groups in Biology                                                                              and Mathematic              Chemistry

and Mathematic                                                              in 1 group

in 1 group

In that way the students did not have to travel one more day during week, which would be exhausting having in mind that day already have obligations at schools during the work days.

Following this principle each student will have 4 tutoring classes in Biology and 4 in Chemistry or Mathematic (depending on the type of studies a student want to enter), or 8 tutor support classes in total per month. During 4 months of the tutoring component, each student will have 16 support classes from the professors at the Faculties of Medicine.

As tutoring classes are taking place from 15-17h and there are 13 students in Novi Sad and 12 students in Nis preparing for the Faculties of Medicine for biology in each city as well for chemistry, 2 professors have been hired by the Faculty of Medicine and one math professor in each city. In total, there are 5 university professors in Nis and 5 in Novi Sad, making the total of 10 tutors.

For both Faculties of Medicine, tutors are the same persons who are engaged by the Faculties of Medicine to conduct group preparatory classes which we find as a benefit for the students for two reasons:

- Teachers are able to get to know each  student better (difficulties, capacity and efforts)

- Teachers who are conducting the group preparatory course and tutoring classes are the ones organizing the entrance exam, so they are more aware of what students should be concentrated on.

At the Faculty of Medicine in Novi Sad, tutoring classes started on 11th March, while at the Faculty of Medicine in Nis they started on 17th March.

- Monitoring and evaluation

  - Monitoring Expert’s field visits to students, teachers, parents and tutors

The purpose of the field visits was to check progress of students, determine difficulties and to encourage parents and students to continue with their effort.

On 21st February, at the 9 May Gymnasium in Nis, the monitoring expert had meeting with parents, students and teachers.

On 22nd February,  at the Medical School “Dr Aleksa Savić” in Prokuplje, the field visit of the monitoring expert took place; 6 parents attended.

On 23rd February, in Chemical-Agricultural School in Belgrade, the field visit was attended by 2 parents.

On 25th February, in the premises of the Roma Students Association, a meeting was held with 8 parents.

On 10th March, at the Faculty of Medicine in Nis, a meeting was held with 10 students.

On 11th March, at the Faculty of Medicine in Novi Sad, the monitoring expert had a meeting with 8 students: Sabina Šuki , Dalibor Maksimović, Dejana Šeguljev, Anastazija Kiš Juhas, Ardita Ramadani, Elma Jašari, Sladjana Muratović and Dimić Danijela, while students Nikolina Savić, Tamara Ametović and Aleksandra Petrović where recenica nije zavrsena

The monitoring expert had a separate meeting with tutors: Jovanka Terzić (biology), Nataša Milošević (chemistry), Nataša Milić (chemistry) and Dragana Dorotic (mathematics).

As this day was the first day of tutoring class, the teachers still did not have impression how classes with Roma students are going. They had questions regarding reporting forms.

On 18th March, at the Faculty of Medicine in Novi Sad, a meeting with 13 students took place.

On 24th March, a meeting at the Faculty of Medicine in Nis took place with Roma parents.

On 1st April, with Roma parents Novi Sad recenica nije zavrsena.

  - Student reports

The students intended to be late with their monthly reports. Nevertheless, we received all 54 reports from 27 students until 10th April for the first month of implementation, covering the activity on individual classes to overcome gaps in knowledge.

  - Teacher reports

Teachers had an obligation to send 3 reports in total: the first one first after testing gaps in knowledge and developing the achievements plan, the second one after testing students’ progress at a half (8) undertaken classes, and at the end, after testing the total progress on the course.

In total, 78 reports were received from teachers.

  - The monitoring expert’s report

Based on 54 student reports, 78 teacher reports and the field visits, the monitoring expert composed a monthly report for the Project Manager. A detailed report on 49 pages covered the monitoring activities in March and April, and it was submitted by the monitoring expert to Project Manager.

Conclusions of monitoring expert:

General impression is that all parties are satisfied how the Program is going. Major question raised on the meetings were related to filling in the reporting forms, with technical details regarding reimbursement of the expenses and a possibility to get the RHSP scholarship after students enter the University.

No major misunderstandings have been recorded between teachers and students, as well as absences of students or lack of efforts by the teachers.

Nevertheless, the students started complaining about the pressure they fill due to the large amount of subject matter they need to learn. In the first week of April, it showed on fact that some of the student started with absences on preparatory course.

The students are additionally pressed by the fact that they have more classes than usual in their schools as they need to compensate classes when schools were closed due to huge snowfall in February.

In Novi Sad, on 17th April 2012                                                        Nenad Vladisavljev

Project Manager